## Sheet1
Cost Estimate
Project Name: U COOK IT | Date: | 3.26
Note: Enter your WBS, hours, labor rates, etc. Add/delete rows and columns as needed and check all formulas (bolded below).
| Internal | $/hour | Internal | External | $/hour | External | Total | Non-labor $ | Total Cost
WBS Categories | Labor |  | $ Total | Labor |  | $ Total | Labor
1. Market Research |  |  | 0 |  |  |  | 0 |  | 0
1.1 Planner | 67.5 | 15 | 1012.5 |  |  |  | 1012.5 |  | 1012.5
1.2 Market Coordination | 67.5 | 15 | 1012.5 |  |  |  | 1012.5 |  | 1012.5
2. Financial and accounting | 475.5 | 30 | 14265 |  |  |  | 14265 |  | 14265
3. Hiring |  |  | 0 |  |  |  | 0
0
3.1.1 Web designer 1 |  |  | 0 | 64.16 | 25 | 1604 | 1604 |  | 1604
3.1.2 Web designer 2 |  |  | 0 | 64.16 | 25 | 1604 | 1604 |  | 1604
3.2 App tester expert | 22.5 | 20 | 450 |  |  |  | 450 |  | 450
3.3 Nutritionist |  |  |  | 22.5 | 10 | 225 | 225 |  | 225
3.4 Quality food control expert | 616.67 | 15 | 9250.05 |  |  |  | 9250.05 |  | 9250.05
3.5 Delivery person |  |  |  | 540 | 11 | 5940 | 5940 |  | 5940
4. Storage | [6 empty] | 0 |  | 0
4.1 Storage management | 508.86 | 15 | 7632.9 |  |  |  | 7632.9 |  | 7632.9
5. App feature programming |  |  | 0 | 108.33 | 60 | 6499.8 | 6499.8 |  | 6499.8
6. Marketing | [6 empty] | 0 |  | 0
6.1 Marketing specialist 1 | 515.44 | 16 | 8247.04 |  |  |  | 8247.04 |  | 8247.04
6.1 Marketing Specialist 2 | 515.44 | 16 | 8247.04 |  |  |  | 8247.04 |  | 8247.04
7. Supplies |  |  | 0 |  |  |  | 0 |  | 0
7.1 Package management | 498 | 18 | 8964 |  |  |  | 8964 | 1000 | 9964
7.2 Monitor | 512 | 18 | 9216 |  |  |  | 9216 |  | 9216
8. IT capability |  |  | 0 |  |  |  | 0 |  | 0
8.1 IT supports | 180 | 15 | 2700 |  |  |  | 2700 |  | 2700
8.2 Download Capabilities | 180 | 15 | 2700 |  |  |  | 2700 |  | 2700
8.3 Data Storage (server & cloud) | 180 | 15 | 2700 |  |  |  | 2700 |  | 2700
9. Beta testing/ pre market launch | 31.65 | 15 | 474.75 |  |  |  | 474.75 |  | 474.75
10. Stakeholder Communication | 540 | 20 | 10800 |  |  |  | 10800 |  | 10800
Subtotal |  |  | 0 |  |  |  | 0 |  | 104544.58
Reserves |  |  | 0 |  |  | 0 | 0 |  | 10454.458
Total | 4911.06 |  | 87671.78 | 799.15 | 131 | 15872.8 | 103544.58 | 1000 | 114999.038
Assumptions
Some working hourly salaries are $15-$20, because $15-$20 are basic salaries in the U.S.
Some working hourly salaries are $18-$30, because $18-$30 should pay for those professional jobs to hire employees.
Some working hourly salaries are $60, because the company may hire external professional expert to solely responsible for programming
Working hours are determined by the estimated time required to achieve each task and the consistency of the tasks