## Sheet1
Cost Baseline
Project Name: U COOK IT | Date: | 3.26
Note: Enter your WBS and costs each month. Add/delete rows and columns as needed and check all formulas (bolded below).
Month
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Total Cost
WBS Categories
1. Market Research | [12 empty] | $ -
1.1 Planner | 337 | 338 | 338 | [9 empty] | 1013
1.2 Market coordination | 337 | 338 | 338 | [9 empty] | 1013
2. Financial and accounting | 1955 | 1955 | 1955 | 936 | 933 | 933 | 933 | 933 | 933 | 933 | 933 | 933 | 14265
3. Hiring
3.1 Desginer
3.1.1 Web designer 1 |  | 534 | 535 | 535 | [8 empty] | 1604
3.1.2 Web designer 2 |  | 534 | 535 | 535 | [8 empty] | 1604
3.2 App tester expert |  |  |  |  | 225 | 225 | [6 empty] | 450
3.3 Nutritionist |  |  | 112 | 113 | [8 empty] | 225
3.4 Quality food control expert | [6 empty] | 1540 | 1541 | 1542 | 1542 | 1542 | 1543 | 9250
3.5 Delivery person | [6 empty] | 990 | 990 | 990 | 990 | 990 | 990 | 5940
4. Storage | [12 empty] | $ -
4.1 Storage management | [6 empty] | 1272 | 1272 | 1272 | 1272 | 1272 | 1273 | 7633
5. App feature programming |  | 2166 | 2167 | 2167 | [8 empty] | 6500
6. Marketing | [12 empty] | $ -
6.1 Marketing specialist 1 |  |  |  |  | 1030 | 1030 | 1030 | 1030 | 1030 | 1032 | 1032 | 1033 | 8247
6.1 Marketing specialist 2 |  |  |  |  | 1030 | 1030 | 1030 | 1030 | 1030 | 1032 | 1032 | 1033 | 8247
7. Supplies | [12 empty] | $ -
7.1 Package management | [6 empty] | 1660 | 1660 | 1660 | 1660 | 1662 | 1662 | 9964
7.2 Monitor | [6 empty] | 1536 | 1536 | 1536 | 1536 | 1536 | 1536 | 9216
8. IT capability | [12 empty] | $ -
8.1 IT supports | [6 empty] | 450 | 450 | 450 | 450 | 450 | 450 | 2700
8.2 Download Capabilities |  |  |  |  | 1350 | 1350 | [6 empty] | 2700
8.3 Data Storage (server & cloud) | [5 empty] | 385 | 385 | 385 | 385 | 385 | 385 | 390 | 2700
9. Beta testing/ pre market launch | [5 empty] | 240 | 235 | [5 empty] | 475
10. Stakeholder Communication | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 10800
Subtotal | [12 empty] | 104546
Reserves | [11 empty] | 10454.6 | 10454.6
Total | 3529 | 6765 | 6880 | 5186 | 5468 | 6093 | 11961 | 11727 | 11728 | 11732 | 11734 | 22197.6 | 115000.6